## Issues
ID | Initiated by | Date Submitted | Meeting Submitted | Topic | Profile Name | Description | Proposed Resolution | Decision | Meeting Decision Discussed | CIM Issue | Doc Update | Profile Update | Enum | Other | Resolution Date | Person Assigned | Due Date | Priority Group | Status | Priority
162 | Jed | 2024-11-13 |  | Data Model |  | Set up and manage the version control system - GitLab/Redmin/Github - EA date model - EA Protobuf Generator source code |  | [2024-11-25] Stuart will confirm with UCAIug whether to use GitLab or GitHub | [9 empty] | Operational | Open
161 | Neil, Curtis, Owen, Chirath, Jed, Mike and Shawn | 2024-10-30 |  | Team Meeting |  | From Mike: Notes from Today's Call: • Owen has provided documentation on the initial updates for 2.2 that we did last year and earlier this year. Please review them for completeness an linkage to the 2.2 changes. We'll see if anyone has any questions/feedback and then accept them at the next meeting. o Document: OpenFMB 2.2.1 EVSEModule Release Draft 20241023.docx o Data Model: OpenFMB Operational Model (61850-CIM) (v2.2.1).eapx • Neil has been advocating changes/additions to the data model to fill in gaps and or correct issues both with 2.2 and earlier. He is going to be completing the documentation over the next two weeks. o Shawn mentioned adding these items to the OpenFMB Issues List. That will be the catalyst to review all these items and get them added. • The SLACK site where we have various strategic documentation about OpenFMB, etc. does not seem to be available to anyone. I'll figure out with Stuart how to get access to the content. As pointed out in the meeting, the subscription might have expired, so we might just need to pay the bills. We'll investigate and try to get it up and running by next time. • Stuart and I will both bug UCA about the website. • Chirath had questions about FLISR. He will send those to Stuart with a copy to me. We'll then discuss in the meeting next time. | [12 empty] | Closed
160 | Chirath | 2024-08-22 |  | Data Model |  | Proposed to extend OpenFMB 2.1 information model for distributed FLISR use case | [12 empty] | Open
159 | Mike, Neil, Owen, Shawn, Seth Gossler, Chirath Pathiravasam, Dmitry, and Jed | 2024-08-21 |  | Data Model |  | 1) Alarm into status for ZGEN and EVSE a. Dmitry questioned if all applicable to all kinds of devices b. Shawn pointed out that the original requirement coming from Larry back on 10/18/2021, most likely from Duke 2) Environmental reading into meter reading a. Existing MENV and MMET LN classes b. Seth provided a use case for this, mainly for ESS c. Shawn recommended to start with use case and requirements for a top-down approach. 3) DC into reading (AC vs. DC) a. Jed: for in front meter so all AC. DC is not part of OpenFMB b. Dmitry to look into this DC thing. | [12 empty] | Open
158 | Neil | 2024-07-17 |  | Data Model |  | Neil's model (not sure if it has been merged) . Extend the ESS Status Profile and the Event Profile to include Alrm: AlrmKind [0..1] 2. Introduce new module: environmentmodule - EnvironmentReadingProfile: - ReadingMessageInfo - EnvironmentSensor - description - mrid - NamedObject - name - EnvironmentReading - ReadingMENV - (combined "MENV=environmental information" and "MMET=Meteorological information" logical nodes) - CO2Em: MV [0..1] - Emission level of CO2 - IEC 61850-7-4.LNClass.MENV.CO2Em - CloudCvr: MV [0..1] - Cloud cover level - IEC 61850-7-4.LNClass.MMET.CloudCvr - DctInsol: MV [0..1] - Direct normal insolation (insolation SIUnit [W/m2]) - IEC 61850-7-4.LNClass.MMET.DctInsol - DffInsol: MV [0..1] - Diffuse insolation (insolation SIUnit [W/m2]) - IEC 61850-7-4.LNClass.MMET.DffInsol - DlDur: MV [0..1] - Daylight duration (time elapsed between sunrise and sunset) - IEC 61850-7-4.LNClass.MMET.DlDur - EnvHum: MV [0..1] - Humidity of environment (typically in %) - IEC 61850-7-4.LNClass.MMET.EnvHum - EnvPres: MV [0..1] - Barometric pressure of environment - IEC 61850-7-4.LNClass.MMET.EnvPres - EnvTmp: MV [0..1] - Temperature of environment [°C] - IEC 61850-7-4.LNClass.MMET.EnvTmp - HorInsol: MV [0..1] - Total horizontal insolation (insolation SIUnit [W/m2]) - IEC 61850-7-4.LNClass.MMET.HorInsol - HorWdDir: MV [0..1] - Total horizontal wind direction - IEC 61850-7-4.LNClass.MMET.HorWdDir - HorWdSpd: MV [0..1] - Average horizontal wind speed - IEC 61850-7-4.LNClass.MMET.HorWdSpd - RnFll: MV [0..1] - Rainfall (typically in mm - length SIUnit [m]) - IEC 61850-7-4.LNClass.MMET.RnFll - SnwFll: MV [0..1] - Snowfall (typically in mm - length SIUnit [m]) - IEC 61850-7-4.LNClass.MMET.SnwFll - VerWdDir: MV [0..1] - Vertical wind direction - IEC 61850-7-4.LNClass.MMET.VerWdDir - VerWdSpd: MV [0..1] - Average vertical wind speed - IEC 61850-7-4.LNClass.MMET.VerWdSpd - WdGustSpd: MV [0..1] - Maximum wind gust speed - IEC 61850-7-4.LNClass.MMET.WdGustSpd - *HumSv:SAV [0..1] - Sampled humidity measurement [%] - IEC 61850-7-4.LNClass.THUM.HumSv - *PresSv:SAV [0..1] - Sampled pressure of media measurement [Pa] - IEC 61850-7-4.LNClass.TPRS.PresSv - *TmpSv:SAV [0..1] - Sampled temperature measurement [°C] - IEC 61850-7-4.LNClass.TTMP.TmpSv - Pres: MV [0..1] - Measured pressure - IEC 61850-7-4.LNClass.SPRS.Pres - Tmp: MV [0..1] - Measured temperature (typically in °C) - IEC 61850-7-4.LNClass.STMP.Tmp 3. Add DC measurement to all reading profiles - ReadingMMDC - Amp: MV [0..1] - DC current - IEC 61850-7-4.LNClass.MMDC.Amp - Ris: MV [0..1] - Resistance in DC circuit - IEC 61850-7-4.LNClass.MMDC.Ris - RisNgGnd: MV [0..1] - DC resistance between negative pole and earth - IEC 61850-7-4.LNClass.MMDC.RisNgGnd - RisPsGnd: MV [0..1] - DC resistance between positive pole and earth - IEC 61850-7-4.LNClass.MMDC.RisPsGnd - Vol: MV [0..1] - DC voltage - IEC 61850-7-4.LNClass.MMDC.Vol - VolNgGnd: MV [0..1] - DC voltage between negative pole and earth - IEC 61850-7-4.LNClass.MMDC.VolNgGnd - VolPsGnd: MV [0..1] - DC voltage between positive pole and earth - IEC 61850-7-4.LNClass.MMDC.VolPsGnd - Watt: MV [0..1] - DC power - IEC 61850-7-4.LNClass.MMDC.Watt 4. Add Topology and Connectivity Information Location - Point that can be defined with one or more 'PositionPoint' in a given 'CoordinateSystem' - IEC CIM.IEC61968.Common.Location dir: String [0..1] - Cardinal (N, E, S, W), Intercardinal Directions (NE, SE, SW, NW), or Sec Intercardinal Directions (NNE, ENE, ESE, SSE, SSW, WSW, WNW, NNW) - IEC CIM.IEC61968.Common.Location.direction addr: StreetAddress [0..1] - Main address of the location - IEC CIM.IEC61968.Common.Location.mainAddress PositionPoint - Set of spatial coordinates that determine a point, defined in the coordinate system specified in 'CoordinateSystem' - IEC CIM.IEC61968.Common.PositionPoint elevation: String [0..1] - Z-coordinate (e.g., elevation or altitude) - IEC CIM.IEC61968.Common.PositionPoint.zPosition latitude: String [0..1] - Y-coordinate (e.g., latitude) - IEC CIM.IEC61968.Common.PositionPoint.yPosition longitude: String [0..1] - X-coordinate (e.g., longitude) - IEC CIM.IEC61968.Common.PositionPoint.xPosition SeqNum: Int [0..1] - Zero-relative sequence number of this point within a series of points - IEC CIM.IEC61968.Common.PositionPoint.sequenceNumber CoordinateSystem - Coordinate reference system (https://epsg.org/) - IEC CIM.IEC61968.Common.CoordinateSystem crsUrn: String [0..1] - A Uniform Resource Name (URN) for the coordinate reference system (CRS) used to define 'PositionPoints' - IEC CIM.IEC61968.Common.CoordinateSystem.crsUrn StreetAddress - General purpose street address information - IEC CIM.IEC61968.Common.StreetAddress streetDetail: StreetDetail [0..1] - Street detail - IEC CIM.IEC61968.Common.StreetAddress.streetDetail townDetail: TownDetail [0..1] - Town detail - IEC CIM.IEC61968.Common.StreetAddress.townDetail StreetDetail - Street details, in the context of address - IEC CIM.IEC61968.Common.StreetDetail code: String [0..1] - (if applicable) Utilities often make use of external reference systems, such as those of the town-planner's department or surveyor general's mapping system, that allocate global reference codes to streets. - IEC CIM.IEC61968.Common.StreetDetail.code name: String [0..1] - Name of the street - IEC CIM.IEC61968.Common.StreetDetail.name number: String [0..1] - Designator of the specific location on the street - IEC CIM.IEC61968.Common.StreetDetail.number prefix: String [0..1] - Prefix to the street name. (North, South, East, West, etc.) - IEC CIM.IEC61968.Common.StreetDetail.prefix Suffix: String [0..1] - Suffix to the street name. (North, South, East, West, etc.) - IEC CIM.IEC61968.Common.StreetDetail.suffix type: String [0..1] - Type of street. (street, circle, boulevard, avenue, road, drive, etc.) - IEC CIM.IEC61968.Common.StreetDetail.type TownDetail - Town details, in the context of address name: String [0..1] - Town name - IEC CIM.IEC61968.Common.TownDetail.name section: String [0..1] - Town section - IEC CIM.IEC61968.Common.TownDetail.section stateOrProvince: String [0..1] - Name of the state or province - IEC CIM.IEC61968.Common.TownDetail.stateOrProvince ConnectivityNodeContainer - A base class for all objects that may contain connectivity nodes or topological nodes connectivityNodes: ConnectivityNode - IEC CIM.IEC61970.Base.Core.ConnectivityNode ConnectivityNode - Connectivity nodes are points where terminals of AC conducting equipment are connected together with zero impedance. terminals: Terminals - IEC CIM.IEC61970.Base.Core.Terminal topologicalNodes: TopologicalNode - IEC CIM.IEC61970.Base.Topology.TopologicalNode BusNameMarker - Used to apply user standard names to topology buses. Typically used for "bus/branch" case generation. Associated with one or more terminals that are normally connected with the bus name. topologicalNodes: TopologicalNode - IEC CIM.IEC61970.Base.Topology.TopologicalNode TopologicalNode - For a detailed substation model a topological node is a set of connectivity nodes that, in the current network state, are connected together through any type of closed switches, including jumpers. Topological nodes change as the current network state changes (i.e., switches, breakers, etc. change state). For a planning model, switch statuses are not used to form topological nodes. Instead they are manually created or deleted in a model builder tool. Topological nodes maintained this way are also called "busses". connectivityNodes: ConnectivityNode - IEC CIM.IEC61970.Base.Core.ConnectivityNode topologicalIsland: TopologicalIsland - IEC CIM.IEC61970.Base.Topology.TopologicalIsland TopologicalIsland - An electrically connected subset of the network. Topological islands can change as the current network state changes: e.g. due to - disconnect switches or breakers change state in a SCADA/EMS topologicalIsland: TopologicalIsland - IEC CIM.IEC61970.Base.Topology.TopologicalIsland | [12 empty] | Open
157 | Neil | 2024-07-17 |  | Data Model |  | Neil proposed the followings: 1. Extend the ESS Status and Event Profiles to include Alarm. a. Currently Alarm: AlrmKind [0..1] is found in i. SolarEventAndStatusZGEN ii. GenerationEventAndStatusZGEN b. Given the nature of the ESS Module this may need to go in both b.i and b.ii below to cover an ESS as both a generation source and as a load i. ESSEventAndStatusZGEN ii. EssStatusZBAT 2. Create a new Environment Module with aspects taken from IEC 61850 related to weather, temperature, humidity, CO2, etc. that is to be used with various sensors. 3. Extend the Reading Profile for all devices to include MMDC – DC Measurements to all Reading Profiles 4. Incorporate a Topology and Connectivity Class to provide some GIS data for a device (GPS coordinates, address, etc.) and define the connectivity of a system. a. The Classes are defined in the text file along with some notes on the object. | [12 empty] | Closed
156 | Mike | 2024-06-17 |  | Data Model |  | Compatibility question With 2.0 to 2.1, we broke the following profiles. - ESS: - ESSControlProfile - ESSStatusProfile - Generation: - GenerationControlProfile - GenerationStatusProfile - Solar: - SolarControlProfile - SolarStatusProfile For 2.2 The major change is the EVSE profiles but there is one more update proposed by Neil and updated by Owen on 3/18/2024. RegulatorEventAndStatusATCC , add attributes: (proposed by Neil) - VolLmtMod - DirMod | [12 empty] | Closed
155 | Cory | 2024-04-30 |  | Data Model |  | EVSEPoint: - 7 listed as reserved but being used for rampRates field EVSEPointStatus: - 7,8, and 9 listed as reserved but being used for rampRates, noRestricEnable, and chargeControlEnable EVACConnectionStateKind: - space in "EVACConnectionStateKind_Not applicable_UNDEFINED" EVACPlugStateKind: - space in "EVACPlugStateKind_Not applicable_UNDEFINED" EVACCableCapabilityKind: - space in "EVACCableCapabilityKind_Not applicable_UNDEFINED" EVConnectionChargingKind: - space in "EVConnectionChargingKind_Not applicable_UNDEFINED" EVDCCableCapabilityKind: - space and hyphen in fields EVDCConnectionStateAKind: - space, hyphen, and "`" (prime) EVDCConnectionStateCKind: - space EVDCPlugStateKind: - space Also, protobuf requires the first field of enum to have 0 value. So, I think to make it consistent with all other enums, the "..._Not applicable_UNDEFINED" fields should have value 0 instead of 98 and move to first field of the enums. [Owen fixed the problems]: 11. EVSEPoint: - ProtobuTag_Reserved value: 2,5,6,8,9,12,14,15 12. EVSEPointStatus - ProtobuTag_Reserved value: 2,5,6,8,9,12,14,15 - noRestricEnable Tag 827 - chargeControlEnable Tag 928 1. EVACCableCapabilityKind - 63-70A  “63to70A - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 2. EVACConnectionStateKind - Removed all space - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 3. EVACPlugStateKind - Connected and Unlocked ConnectedandUnlocked - Connected and locked ConnectedandLocked - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 4. EVConnectionChargingKind - Removed all space - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 5. EVDCCableCapabilityKind - 16-20A 16to20A - 30-32A 30to32A - 60-63A 60to63A - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 6. EVDCConnetionStateAKind - All hyphen, and "`" (prime)Underscore”_” - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 7. EVDCConnectionStateKind - Removed all space - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) 8. EVDCPlugStateKind - Connected and Unlocked ConnectedandUnlocked - Connected and locked ConnectedandLocked - Not applicable_UNDEFINED (initial value: 98)UNDEFINED (initial value: 0) | [12 empty] | Closed
154 | Owen | 2024-03-17 |  | Data Model |  | Owen shared the model he updated on 3/17/2024 . RegulatorEventAndStatusATCC , add attributes: (proposed by Neil) - VolLmtMod - DirMod 2. EVSEReadingProfile, add LNs: - PhaseMMTN - ReadingMMTN 3. EVSEPoint, add attributes: - rampRates - wOperation 4. EVSEStatusProfile, add LN: EVSEPointStatus | [12 empty] | Closed
153 | Owen | 2024-02-26 |  | Data Model |  | 1. Add MMTN in EVSE Reading Profile 2. In EVSE Control Profile, add 3 attributes. • chargermode: ChargerModeKind[0..1] NoRestrictions 1 Will always charge an EV when plugged in with no restrictions. CloudAPI 2 Globally-applied settings to either enable or disable charging, or set restrictions that apply to every new plug session (if enabled). ChargeWindows 3 enabling scheduling of EV charging OCPP 4 OCPP is used as the communication protocol with the charger ManualOverride 5 Temporarily override any configured settings. Can only be entered via physical interaction with the unit. • maxCurrent: FLOAT32 [0..1] (The maximum amount of current that a plugged-in vehicle will be allowed to pull, in Amps.) • maxEnergy: FLOAT32 [0..1] (The maximum amount of energy that a plugged-in vehicle will be allowed to consume, in watt-hours.) | [12 empty] | Closed
152 | Jerry | 2023-12-12 |  | Data Model |  | 1. Replaced illegal chars with underscore "_": - EVACCableCapabilityKind - EVACCableCapabilityKind_63/70A => EVACCableCapabilityKind_63_70A - EVACCableCapabilityKind_Not applicable / Unknown => EVACCableCapabilityKind_UNDEFINED. Notes: - Rename all "*_Not applicable / Unknown" to "*_UNDEFINED" - To be consistent, the tag number should be 0 for all "*_UNDEFINED" - EVACPlugStateKind - EVDCPlugStateKind - EVConnectionChargingKind - EVDCCableCapabilityKind - EVDCConnectionStateAKind - EVDCConnectionStateCKind - EVACConnectionStateKind 2. In common module: changed "BOOLEAN" to "boolean" type for all SPG.setVal 3. EVSEPoint: - state is using the reserved number 11 (remove 11 from reserved list); removed 11. 4. Renamed classes to use upper case: - capabilityRatingsDEAO => CapabilityRatingsDEAO - capabilityRatingsDEDO => CapabilityRatingsDEDO | [12 empty] | Closed
151 | Team meeting | 2023-11-27 |  | Data Model |  | 1) Removed “evsemodule – Liberas” package 2) EVSE package namespace issue for XSD generation (missing target namespace) a. Updated all version to 2.2 b. No namespace change to the existing modules 3) Double checked IEC61850 duplicates a. Added missing “trace” associations between the new EVSE classes and IEC61850 classes 4) Moved the following classes from ESSModule to CommonModule a. CapacityFirming b. FrequencyRegulation c. PeakShaving d. SocLimit e. SOCManagement f. VoltageDroop g. VoltagePI h. VoltageRegulation | [12 empty] | Closed
150 | Owen | 2023-10-31 |  | Data Model |  | Owen updated the data model and uploaded to Basecamp | [12 empty] | Closed
149 | Shawn H. | 2023-10-24 |  | Data Model |  | Model Updates: - Added new package “Electric Vehicle Supply Equipment (EVSE) Use Cases” and sub package, “Configure Limit Active Power Level”. - Added new actors: o Utility o Charging Station Management System (CSMS) o Charging Station (CS) o CPO - Added use case and activity diagram Owen also updating the model, so need find a way to merge (see his email on 10/24/2023) | [12 empty] | Closed
148 | Owen | 2023-10-23 |  | Data Model |  | Owen updated the data model and uploaded to Basecamp | [12 empty] | Closed
147 | Neil, Owen, Nick, Shawn, Jerry, Stuart, Rosanna, Jed | 2023-10-16 |  | Data Model |  | Status report: • Capability and CapabilityOverride profiles o Followed OpenFMB capability profile model pattern to have 2 classes:  CapabilityRatings (immutable)  CapabilityConfiguration (mutable) o Special: extra class – capabilityRatingsZCAB • Reading profile o Followed OpenFMB reading profile pattern:  MMXU  MMTR o Special: extra class - EVSEReadingDESE • Status & Event profiles o Event – for unsolicited (not asked for) o Status – usually a reply for a control message • Control profile o Nick to provide | [12 empty] | Closed
146 | Nick, Owen, Neil, and Shawn | 2023-09-15 |  | Data Model |  | • Merged EVSECapabilityProfile & EVSECapabilityOverrideProfile o Last meeting update looks good, no further update needed • Worked on EVSEControlProfile o ZCAB not needed (Owen) since cables are not controllable o Removed ControlDEEV LN classes since it is not controllable o Related classed also removed o Question about the transId (keep it for now) o Control profile is a valid use case that evse chanrging can be remotely controlled and queued o Owen: control is usually set max values o Nick: Cost related information should be at adaptor level, not information model level • Sequence diagram discussed (triggered by Neil’s email a couple of days ago regarding of the weather profile) o Nick shared a sequence diagram from OCPP standards | [12 empty] | Closed
145 | Nick, Owen, Neil, and Shawn | 2023-09-13 |  | Data Model |  | • Merged EVSEStatusProfile & EVSEEventProfile o Based on Eaton model o Shared Status and Event LN classes • Worked on EVSECapabilityProfile o Removed DEEV LN classes since it is not configurable | [12 empty] | Closed
144 | Nick, Owen, Neil, and Shawn | 2023-09-11 |  | Data Model |  | • Merged EVSEReadingProfile o Based on Eaton model o Role evseReadingDESE multiplicity changed to 0..* o ReadingDEAO and DEDO multiplicity changed to 0..1 • Worked on EVSEStatusProfile o Proposed to merge Status and Event profiles o Role statusDESE multiplicity changed to 0..* | [12 empty] | Closed
143 | Owen, Neil (OES), Stuart, and Shawn | 2023-08-15 |  | Data Model |  | • Copied EATON model to v2.2 and 61850 RM Owen hand built • Copied both Liberas and EATON models to a Word document <<Model Diff - Eaton vs. Liberas.docx>> for comparison and for team discussion | [12 empty] | Closed
142 | Stuart, Mike, Owen, Nick, Duncan, Emile, Rosanna, Jed, Yazan, and Shawn | 2023-07-24 |  | Data Model |  | Nick presented his EVSE model Owen presented his EVSE model | [12 empty] | Closed
141 | Mike, Stuart, Shawn, Emile, Nick, Owen Wu, Tanya Krackovic (Hamilton, Liberas), Jed, Dmitry, Yazan | 2023-06-22 |  | Data Model |  | OpenFMB v2.2 model kick off Two models, one from Eaton and one from Liberas, need to be integrated. [Emile]: Proposed to start with use cases for EVSE (also needed for grid codes before but no enough time at that time). [Stuart]: Proposed for v2.2 not just for EV but also other topics such as FLISR (See Jed comments in 2022) [Mike]: Concern about more and more added to the scope based on the v2.0 experience | [12 empty] | Closed
140 | Mike Burck | 2023-05-08 |  | Data Model |  | Summary from Shawn: Here is a list of major changes made to v2.1 • Grid codes functions added into DER related control profiles such as ESSControl and SolarControl o Relevant Status and Event profiles updated • Capacity and CapacityOverride profiles added • Bug fixes and model improvement V2.1 freeze on 5/10/2023 | [12 empty] | Closed
139 | Emile | 2023-04-25 |  | Data Model |  | In SolarDiscreteControlProfile, would it be possible to add the label (or whatever it’s called) from SolarDiscreteControlProfile to SolarDiscreteControl like we usually have. | [12 empty] | Closed
138 | Dwayne & Shawn | 2023-04-03 |  | Data Model |  | Residual current, as the algebraic sum of the instantaneous values of currents flowing through all live conductors of a circuit at one point of the electrical installation ('phsA.instCVal'+'phsB.instCVal'+'phsC.instCVal'). | [12 empty] | Closed
137 | Dwayne & Shawn | 2023-03-02 |  | Data Model |  | From Dwayne: • WSPC is defined in "essmodule" but it is also being used in "solarmodule" now. We need to move WSPC to "commonmodule" so it can be shared correctly. • SolarPoint.wOperation has a ProtobufTag=23 but that value is also set in the ProtobufTag_Reserved list for SolarPoint. We either need to change the ProtobufTag to a new number or remove that value from the ProtobufTag_Reserved list. I'm not sure which should be done here since I'm not looking at the previous data model. Is that something that you could double-check? Shawn: • Moved WSPC to “commonmodule” package. • Change SolarPoint.wOperation tag value to 24. Dwayne: Move OperationDWGC to commonmodule as well. | [12 empty] | Closed
136 | Dwayne & Shawn | 2023-03-01 |  | Data Model |  | Updated the OpenFMB model after an email from Dwayne to use ProtobufTag_Reserved • Updated ESSPoint ProtobufTag_Reservced tag • Updated SolarPoint following the ESSPoint update (wOperation added, and attributes removed following ESSPoint update, and also ProtobufTag_Reserved added). SolarCurvePoint is added into the SolarControlProfile • Added ProtobufTag_Reserved for SolarPoint | [12 empty] | Closed
135 | Emile, Fares, Mike, Jed, Josh, and Shawn | 2023-02-28 |  | Data Model |  | 1. Worked on the list in Mike’s meeting invite: -- COMPLETE... SolarControlProfile constant power factor is mapped differently than ESSControlProfile -- Volt-VAr Vref open-loop response time is mapped to a double instead of a ClearingTime -- OpenFMB does not map well to primary controls -- Double Control Point Needs Documentation/Rename Status: All done. Jed provided notes for both ControlDPC and PhaseDPC. No change to the StatusDPS and PhaseDPS. 2. Worked on the ESSPoint related models: a. Added a new class, ESSCurvePoint, into the ESSControlProfile following the pattern of CapBankControlProfile. Removed the startTime in ESSPoint b. Note the data type of the startTime is “ControlTimestamp”, not “Timestamp”. Question: should the data type of startTime be changed to ControlTimestamp in the CapBankPoint class? This change is not backward compatible. 3. Question to Dwayne, should the ESSPoint attributes be re-tagged after some removed? See the latest ESSPoint at the left. | [12 empty] | Closed
134 | Shawn H. | 2023-02-20 |  | Data Model |  | Shawn transferred the EAP to EAPX. | [12 empty] | Closed
133 | Dwayne | 2023-02-20 |  | Data Model |  | Updates proposed by Dwayne • Rename the following 2 interconnection profiles: o InterconnectionPlannedScheduleProfile o InterconnectionRequestedScheduleProfile • Renamed top class names for the two profiles • Renamed source role names for all related associations Removed the following attributes requested by Emile: • realPwrSetPointEnabled • reactivePwrSetPointEnabled • frequencySetPointEnabled • pctHzDroop • voltageSetPointEnabled • pctVDroop • syncBackToGrid As for the “startTime” attribute, it is kept for now since it is needed for the curve schedule. Let’s discuss this in our next meeting. | [12 empty] | Closed
132 | Dwayne & Stuart | 2023-02-03 |  | Data Model |  | Proposed to add SolarDiscreteControlProfile | [12 empty] | Closed
131 | Dwayne | 2023-02-02 |  | Data Model |  | Propose to rename these 2 interconnection profiles to: InterconnectionPlannedScheduleProfile InterconnectionRequestedScheduleProfile | [12 empty] | Closed
130 | Emile, Stuart, Dwayne, Jed, Mike, Josh, Faire, Shawn | 2023-02-01 |  | Data Model |  | Mainly went through the list from Emile (see item above). The main question is if the ESSPoint should be cleaned up or split. The recommendation from Dwayne and Emile is to clean up the ESSPoint and then add a class between ESSCSG and ESSPoint so that the ESSPoint.startTime can be moved to the new class, similar to the CapBankControl profile (see below). Emile will study the latest 7-420 to see how the ESSPoint can be cleaned up. Right now, there are attributes overlapped such as the ramp and droop fields. Stuart scheduled a meeting with Dmitry to go through some of those. Updated 2 profiles: ESSControlProfile and ESSDiscreteControlProfile Updated OperationDVVR to change VRefTmms data type (used to be a FLOAT32 field) Added ESSDiscreteControlProfile - WSPC and OperationDWGC as Emile recommended Added wOperation into ESSPoint Updated one Grid Code class, OperationDCTE | [12 empty] | Closed
129 | Mike Burck | 2023-01-25 |  | Data Model |  | • SolarControlProfile constant power factor is mapped differently than ESSControlProfile o We first thought that SolarControlProfile didn’t have constant power factor, but it’s actually available under a different name (pFOperation instead of pFStorageOperation). Our controls team said that it makes sense, although we don’t support pFLodTgtMxVal parameters. • Volt-VAr Vref open-loop response time is mapped to a double instead of a ClearingTime o Open-loop response times are usually mapped to commonmodule::ClearingTime in other parameters. For some unknown reason, the Volt-VAr open-loop response time is mapped to a double which we took for granted was a number of milliseconds (because of its name “vreftmms”). • OpenFMB does not map well to primary controls o The driving of the inverter is done by regularly (usually ~20ms) sending active power (P) and reactive power (Q) setpoints. This is a form of primary control that does not really exist in OpenFMB. To accommodate for that, we used ScheduleParameters structure with the ScheduleParameterKind_W_net_mag and ScheduleParameterKind_VAr_net_mag enumeration variants. However, our understanding is that these elements were not designed for this use case. Notably, they appear inside a schedule and therefore requires an execution time. This does not make much sense for driving an inverter in soft real-time. • Double Control Point Needs Documentation/Rename o Click on our UML to see that the DPC “Double Point Controllable ” only has a single bool (a two-state value) in it. Without drilling into that type you don’t notice it, so I was surprised when I went to map it and it didn't match the RTAC. | [12 empty] | Closed
128 | Dwayne | 2023-01-13 |  | Data Model |  | For all of our DiscreteControlProfiles, we always just used the ControlMessageInfo class What I found though is some inconsistencies with the CapabilityProfiles and CapabilityOverrideProfiles. For instance, SolarCapabilityOverrideProfile and GenerationCapabilityOverrideProfile use a CapabilityOverrideMessageInfo class. But, the ESSCapabilityOverrideProfile uses the CapabilityMessageInfo I think that we should just use a single CapabilityMessageInfo class for ESS, Solar and GenerationCapabilityOverrideProfiles. That would be consistent with how we did the Control vs. DiscreteControl profiles as well. We could then just remove the CapabilityOverrideMessageInfo class from the model. [Shawn updated the model accordingly]: • Updated the following models to replace CapabilityOverrideMessageInfo with CapabilityMessageInfo: o GenerationCapabilityOverrideProfile o SolarCapabilityOverrideProfile • Removed the CapabilityOverrideMessageInfo class from the model | [12 empty] | Closed
127 | Dwayne | 2023-01-12 |  | Data Model |  | Dwayne reported a bug. Bug fix to replace the EventMessageInfo with StatusMessageInfo for the CircuitSegmentStatusProfile data model Shawn fixed it and upload to the Basecamp https://3.basecamp.com/3682944/buckets/24628021/uploads/4285954650/versions/new | [12 empty] | Closed
126 | Joshua Hambrick, Neil Shepard, Dwayne, & Shawn | 2022-12-15 |  | Data Model |  | • Team asked Shawn to create the ESSDiscreteControl profile using the CapBankDiscreteControlProfile as an example (see below) • Need to improve the Notes for all classes especially the Grid Codes model. Jed raised another use case for market dispatch and etc. New architecture for reference architecture for new applications, market, rate, dispatch related. OpenFMB is not a protocol, but a data model to enable some functions. It can carry grid codes. Josh mentioned there are other items from Eaton that we have to wait for next meeting, something like mapping to wrong double point instead single | [12 empty] | Closed
125 | Modeling team | 2022-12-07 |  | Data Model |  | Updated ESSControlProfile to replace OperationStorageDFPF and PFStorageSPC with OperationDFPF and PFSPC, respectively. Note that both ESSEventProfile and ESSStatusProfile have been also updated to reflect the change in the corresponding control profile. | [12 empty] | Closed
124 | Larry, Nick, Jed, and Shawn | 2022-03-07 |  | Data Model |  | Nick update the OpenFMB v2.2 to move the classes to 61850-90-8 package Nick also created a separate package under Reference Models for OCPP and import the OCPP 1.6 WSDL into the newly created package (see screen below). Nick imported OCPP v1.6 as a reference model | [12 empty] | Closed
123 | Larry, Dwayne, Nick, and Shawn | 2022-02-08 |  | Data Model |  | - Nick walked through the 61850-90-8 model for EVSE - Created IEC61850-90-8 package in the Reference Models o Added notes as much as possible - Move all LN classes from Nick to the newly generated package - Hard copy needed ones to OpenFMB package and trace to original ones - Trim or extend as needed or merge ones from OCPP model o OCPP model should be created in the Reference Models | [12 empty] | Closed
122 | Larry, Bob, Dwayne, Dmitry, Jed, Casey, and Shawn | 2021-12-06 |  | Data Model |  | • Added missing datatype for OplTmmsMax (type of ClearingTime) o OperationDHFW o OperationDLFW o OperationDVVR o OperationDVWC | [12 empty] | Closed
121 | Larry, Dwayne, Jed, and Shawn | 2021-11-29 |  | Data Model |  | • Renamed CapabilityRatings to SourceCapabilityRatings and CapabilityConfigurarion to SourceCapabilityConfigurarion o [Jed]: Source implies GeneratingUnit, Inverter, Solar, and ESS o Other devices can have different CapabilityRatings • Added two enum classes, AbnOpCatKind and Novocain • Shared the HTML with the team | [12 empty] | Closed
120 | Larry, Bob, Dwayne, Dmitry, Jed, and Shawn | 2021-11-23 |  | Data Model |  | Reviewed the model updates (ESSControlProfile) made yesterday Updated ESSEventProfile and ESSStatusProfile Added the followings from Larry into the ZBAT and the other 10 operations (same as ControlProfile) into ZGEN | [12 empty] | Closed
119 | Larry, Casey, Dwayne, Dmitry, Jed, and Shawn | 2021-11-22 |  | Data Model |  | Updated the Solar profiles after Dwayne’s test on 11/22 (see email) Completed ESSCapabilityProfile and ESSCapabilityOverrideProfile based on the Word document share by Larry (see email on 11/22) • See Constant Power Factor (PFLodTgt) in GenerationControlProfile Note the PFLodTgt is only for Storage so the original OperationDFPF is updated to remove the PFLodTgt field, and added a new class OperationStorageDFPF to inherit from the original one | [12 empty] | Closed
118 | Larry, Dwayne, Jed, Stuart, and Shawn | 2021-11-15 |  | Data Model |  | • Sync up SolarPoint with GenerationPoint • blackStartEnabled and syncBackToGrid added into SolarPoint • [Jed]: SolarPoint should be inherited from GenerationPoint • [Dwayne]: Better to not add the inheritance to maintain the v2.0.0 compatibility • GenerationPointStatus should be sync’d with GenerationPoint (to add behind scene) o Data type concern: should GenPoint APC to GenPointStatus SPS? o Shawn updated the model on 11/17 | [12 empty] | Closed
117 | Larry, Casey Roberts, Dmitry, Dwayne, Bob, Jed and Shawn | 2021-11-05 |  | Data Model |  | [Bob]: Question on if SchedulePoint control values are in pu or absolute. The answer from the team is “absolute” which is the convention for OpenFMB up to this point. This triggered a review of all DER operation classes again to make sure all notes are correct. [Larry]: Keep the FreqNomRtg as a required field in the ratings class Added AMaxRtg as an optional field into GCapP Discussed DFPF.PFExtSet to define the overexcite and underexcite Boolean field [Bob]: Var value can be referenced to VAMax, WMax, or VArMax (SH: do we need a field to specify which max value is in use then?) [Jed]: proposed to use absolute against pu values for all to be consistent. Dwayne and Larry seem supporting that. | [12 empty] | Closed
116 | Larry, Casey Roberts, Dmitry, Dwayne, Jed, Bob, and Shawn | 2021-11-01 |  | Data Model |  | Reviewed GCP, GCOP, GDCP and GCP During the GCP review: o Hz in pu or absolute, agreed to go for pu o Added FreqNomRtg into the CapabilityRating class but not in the config one o But after a review of the DbOf(see below), Larry questioned if the hz should be all in absolute o SchedulePoint was reviewed which all in absolute and per phase o Jed provided 3 options and one of them is to be consistent o Another issue raised by Jed to include AMaxRtg in the CapabilityRating class, this field is not in 1547 but in SunSepec, the argument from 1547 was that it is redundant since it can be derived from VAMax and Vmax. Larry asked to make the field optional if added.  Issue not resolved and pushed to a meeting on Friday (11-12 ET) | [12 empty] | Closed
115 | Larry, Casey Roberts, Dmitry, Dwayne, Jed, Bob, and Shawn | 2021-10-25 |  | Data Model |  | • GenerationDiscretePoint class removed from the GenerationDiscreteControl profile based on the inputs from Jed. • Jed provided Notes for both GenerationDiscreteControlProfile and GenerationControlProfile • Voltage trip and frequency trip profiles updated: o Dmitry: add ClearingTime, instead of using CumulativeTime o Dmitry showed the 61850 using pu for both hz and volt trip values o [SH]: if pu, where to define reference hz (e.g. 60 or 50 hz) value which is not in the capability profile • Since the tmVoltOperation is renamed to tmVoltTripOperation, this operation cannot be reused by “Momentary Cessation”. Larry asked to leave it for later. | [12 empty] | Closed
114 | Larry, Cory, Dwayne, Bob, and Shawn | 2021-10-21 |  | Data Model |  | Discussed the Word document from Larry sent on 10/20. After a discussion between Larry, Dwayne, and Bob, there is no need to change the model since the operation fields are optional and only the ones populated get to write into the Modbus registry (say registry #12). No need to create extra enum or group classes for any mutual exclusive operations. All necessary operations will be populated in a single payload Also discussed is the GenerationDiscreteControl profile. The GenerationControl.GenerationPoint is copied over and needs to be trimmed with Dmitry and Jed are on the call (next Monday’s meeting) Larry questioned why “Momentary Cessation” is not in the Control profile. Shawn explained to him based on the Notes in Dmitry’s Word document on 09/20 “GenerationControlProfile/../GenerationPoint.tmVoltOperation (same as Voltage Trip – time-voltage curve. Cessation status values will be defined in corresponding status profile)”. This will be further discussed with Dmitry on next Monday | [12 empty] | Closed
113 | Larry, Casey Roberts (for Stuart @Duke), Dwayne, David, and Shawn | 2021-10-18 |  | Data Model |  | • Added notes for the GenerationControl operation classes for the pu or absolute value fields • Bob asked if any curve style (CIM term) in the model • The 3 Rtg fields are required in the CapabilityRatings class but cannot be configured, so the 3 corresponding fields (see below) are removed from the CapabilityConfiguration class. [Required]: · AbnOpCatRtg · NorOpCatRtg · ReactSusceptRtg [Deleted]: · AbnOpCat · NorOpCat · ReactSuscept • Updated GenerationStatus to add the remaining classes in Larry’s Word document | [12 empty] | Closed
112 | Larry, Dwayne, Dmitry, and Shawn | 2021-10-14 |  | Data Model |  | Created the new GenerationCapabilityOverrideProfile and updated the GenerationCapabilityProfile. Note the attributes in the CapabilityConfiguration classes are all defined as optional. The top 3 fields in the CapabilityRating need to be discussed with Bob on if they should be optional | [12 empty] | Closed
111 | Larry, Dwayne, Jed, Dmitry, Bob, and Shawn | 2021-10-13 |  | Data Model |  | New Profiles in Generation Module • GenerationCapabilityProfile - A few notes that CapabilityValue class renamed to NameplateValue - Convention to follow 61850 LN not followed for the Capability profile since multiple LN and non 61850 attributes are involved - <<LNClass>> stereotype yet to be removed for these classes | [12 empty] | Closed
110 | Larry, Dwayne, Jed, Shawn | 2021-10-01 |  | Data Model |  | • PU issue discussed. Jed doesn’t think Var is usually in PU • Need both Bob and Dmitry on the call for this PU case. Leave this to Monday meeting • Capability profile is discussed (Dwayne: doesn’t think need to bury this into status and control, capability values are static and not changing usually, need a new profile just for capability) • Team discussed if two separate profile (patterns) needed: <>NameplateProfile (never change) and <>SettingProfile (slow change) o Need further discussion next Monday | [12 empty] | Closed
109 | Larry, Dmitry, Jed, Shawn | 2021-09-27 |  | Data Model |  | Larry presented the reading mapping to MMTU and other LN o [SH]: recommended to replace “MMTU” with “ReadingMMTU” and add column title Discussed Nameplate and capability mapping in Dmitry’s document o AI for Dmitry to screen shot 61850 DGEN for the full list | [12 empty] | Closed
108 | Larry, Dmitry, Dwayne, Jed, Shawn | 2021-09-23 |  | Data Model |  | Larry presented SunSpec spreadsheet 70 tab for if MustTrip and alike are needed to be included in the voltage trip. Dmitry doesn’t think they are needed and no idea why they are in the SunSpec sheet. Recommended to have SunSpec expert to join the meeting. Larry will find out Changed attributes, rtnSrvAuth & rtnSrvAuto, data type to Boolean to align with SunSpec. And later rtnSrvAuth was removed as recommended by Larry. Dmitry think otherwise but ok for now. | [12 empty] | Closed
107 | Larry, Jed, Dmitry, Dwayne, Shawn | 2021-09-20 |  | Data Model |  | Added the following 2 operations - Limit Maximum Active Power - Enter Service | [12 empty] | Closed
106 | Larry, Dmitry, Dwayne, Shawn | 2021-09-17 |  | Data Model |  | 1) Added modEna into OperationDHFW, DLFW, and DFPF as requested by Larry (I noticed that the Hz-W and PF operations do NOT have a ModEna field. Is that intentional? Or should they have ModEna in the "Operation DXXX" class as the others do?) 2) Two more operations (Voltage Trip & Frequency Trip) added including a new data type, CumulativeTime (similar to ControlTimestamp.secondes and nanoseconds) for PTOV/PTUV & PTOH/PTUH, | [12 empty] | Closed
105 | Larry, Dwayne, Dmitry, Shawn | 2021-09-15 |  | Data Model |  | Worked on the 6 following grid code "Operations" - Volt-Var DVVR - W-Var DWVR - Volt-W DVWC - Hz-W DHFW & DLFW - Power Factor DFPF - Var DVAR | [12 empty] | Closed
104 | Larry, Dwayne, Jed, Dmitry, Shawn | 2021-09-13 |  | Data Model |  | Dwayne proposed to create OperationDVVR as a type for the VoltaVarCSG.vVarParamneter | [12 empty] | Closed
103 | Larry, Dwayne, Shawn | 2021-09-10 |  | Data Model |  | Decision to add VVarCrv and VWCrv into the existing GenerationPoint as one curve for a point of time (curve of curve) | [12 empty] | Closed
102 | Larry, Shawn | 2021-09-09 |  | Data Model |  | Larry shared the SunSpecModbus Word document and discussed how to model the 705 tab into OpenFMB. The GenerationControlProfile was used for prototyping. One way to do is to add specialized LN such as GenerationControlDVVR for the ones not currently in the FSCC LN. The droop values are already in the FSCC. The challenge is to group the control related and ride-through related values since they belong to different LN in 61850 | [12 empty] | Closed
101 | Larry, Shawn, Jed, Bryan, and Dmitry | 2021-08-30 |  | Data Model |  | Discussed the DECP.VRef that Larry had a concern on other fields in this LN. For VRef, Shawn proposed to use CIM BaseVoltage. The decision is to leave it out for now. Larry shared << SunSpec_Modbus_IEEE_1547-2018_Profile_20210708.xlsx>> and << SunSpecModbusIEEE_1547-2018.docx>>. The team went through some of the sheets in the Excel. No change to the OpenFMB model in this meeting. | [12 empty] | Closed
100 | Larry, Dmitry, Dwayne, and Shawn | 2021-08-23 |  | Data Model |  | Walked through the ESSCapabilityProfile and SolarCapabilityProfile with the team. Two discussion points: • To add an association between ConductingEquipment and Terminal and make it 0..2 so it is backward compatible. Need to verify this with Cory. o Connectivity profile is mentioned but not in this scope for now • If only DECP.VRef is needed, the CIM BaseVoltage can be copied over (see diagram below). o DECP.VRef is required to cover the IEEE1547 (see icd file from Dmitry) | [12 empty] | Closed
99 | Larry, Cory, Dmitry, & Shawn | 2021-08-16 |  | Data Model |  | 1) Need discussion to see where the Terminal should be modeled. The use case is for a generating unit to reference a DECP/VRef for the electric connection point (ECP) 2) Add LPHD attributes (vendor, model, sernum, swRev) into CapabilityValue class 3) DSTO only applies to ESS module which should include DGEN as well | [12 empty] | Closed
98 | Modeling Team | 2021-04-27 |  | Data Model |  | 1) Clean up the notes for the following 3 requirement packages: a. Interconnection Related b. Reserve Related c. Circuit Segment Service Related 2) Removed Non-function requirements package. 3) Added the following notes into the circuitsegmentservicemodule, reservemodule and interconnectionmodule: a. “This module is an early alpha release and subject to change. It is NOT part of the gateway test procedure for OpenFMB certification.” [Reported from Larry]: Removed “Generation Forecaster” actor. | [12 empty] | Closed
97 | Stuart L. | 2021-04-26 |  | Data Model |  | Replace “Coordination” with “CircuitSegment” per request from Stuart on 4/23 and confirmed on 4/26. This change involves name change in data models, sequence diagrams and requirements packages. | [12 empty] | Closed
96 | Larry & Shawn | 2021-04-05 |  | Data Model |  | Work session (Larry & Shawn) • Cleaned up all data models to hide unnecessary data type classes. | [12 empty] | Closed
95 | Dwayne, Larry, Stuart, and Shawn | 2021-04-02 |  | Use Case |  | Work session (Dwayne, Larry, Stuart, and Shawn) on Phase 1 and Phase 2 use-cases that point to the requirements layer that might not be updated to align with Phase 3 (DER circuit segment management) and UML 2.0 data models. The following model packages have been updated to align with the Use Cases and Data Models: • Actors • Requirements • Sequence Diagrams | [12 empty] | Closed
94 | Shawn H. | 2021-03-31 |  | Data Model |  | OpenFMB model updated: • Renamed to “Apache License, Version 2.0” • Removed Linked Document for both classes in the License and Copyright diagram Mass replacement performed for the full model: “OpenFMB Operational Model (61850-CIM) (v2.0.0) - Full model (mass replcmnt).eap” Python scripts can be found at: C:\Users\ShawnHu\AppData\Local\Programs\Python\Python39 | [12 empty] | Closed
93 | Shawn H. | 2021-03-30 |  | Data Model |  | OpenFMB model updated: • Version, Phase, and Language are replaced accordingly: o Version=2.0.0 o Phase=2.0 o Language=”” • Diagram “Author” updated | [12 empty] | Closed
92 | Shawn H. | 2021-03-29 |  | Data Model |  | OpenFMB model updated: • Removed both IEC CIM and 61850 reference model packages • Removed the NAESB diagrams package • Mass replaced Author name with “OpenFMB” | [12 empty] | Closed
91 | Dwayne, Larry, and Shawn | 2021-03-19 |  | Data Model |  | Work session with Dwayne, Larry, and Shawn for the issue reported by Dwayne on 01/05/2021 - Updated Copyright o Author name changed to “OpenFMB” o Date changed to 2021 - Namespaces in all packages have been updated to 2021/04 - Reference Models and NAESB packages will be removed before official v2 release o The whole model with the 2 packages has been posted on the Basecamp - Shawn to research if a mass replacement is possible to replace Author, Version, and Language | [12 empty] | Closed
90 | Dwayne, Larry, and Shawn | 2020-12-14 |  | Data Model |  | 1) Updated CapBankControlProfile/CapBankControlYPSH and CapBankStatus (&Event)Profile / CapBankEventAndStatusYPSH to add the attributes for AMP, Ctl, Vol, VAr, and Temp. Also the existing POS (in the control class) data type changed to PhaseSPC (used to be PhaseDPC), no change to the Status&Event class 2) Updated CapBankDiscreteControlProfile to reuse the CapBankControlYPSH 3) Added a “secondaryReadingMMXU” in the CapBankReadingProfile 4) Time limits and Voltage alarm thresholds are ignored. | [12 empty] | Closed
89 | Dwayne, Larry, and Shawn | 2020-12-03 |  | Data Model |  | 1) Updated the followings to change from ControlDPC to ControlSPC and StatusDPS to StatusSPS a. ESSPoint / ESSPointStatus b. GenerationPoint / GenerationPointStatus c. SolarPoint / SolarPointStatus d. LoadPoint / LoadPointStatus e. InterconnectionPoint 2) Changed CoordinationStatusDCSC/Island data type from StatusSPS to StatusDPS 3) Changed RegulatorEventAndStatusATCC/voltageSetPointEnabled data type from StatusSPC to StatusSPS 4) Removed StatusSPC 5) Updated the notes for the following fields in the RegulatorEventAndStatusATCC a. BndWidHi & BndWidLo b. VolLmtHi & VolLmtLo c. DirRev & DirCtlRev | [12 empty] | Closed
88 | Dwayne, Larry, and Shawn | 2020-11-30 |  | Data Model |  | Updated RegulatorDiscreteControlATCC: • Added 61850 native attributes, TapOpL and TapOpR, back into the ATCC class but data type changed to PhaseSPC. • Removed TapPos from the RegulatorControlATCC, but kept in the corresponding status/event class (RegulatorEventAndStatusATCC). • After the update: Updated RegulatorReadingProfile: • Added an extra association between RegulatorReading and ReadingMMXU with target role name as “secondaryReadingMMXU”. • After the update: Updated RegulatorStatus(& Event)Profile • Added the following attributes into RegulatorEventAndStatusATCC class: o BndWidHi o BndWidLo o VolLmtHi o VolLmtLo o DirRev o DirCtlRev o DirIntd | [12 empty] | Closed
87 | Dwayne & Larry | 2020-11-24 |  | Data Model |  | Enum update requested by Dwayne and Larry (see item above) - Add UNDEFINED if missing (keep "none") - Keep the previous sequence order - Exception: no change to PhaseCodeKind and UnitSymbolKind numbering which are part of the IEC CIM standard. Split RegulatorControlATCC into 2 classes (RegulatorControlATCC and DirectionalATCC), added 2 new enum classes (DirectionModeKind and VoltLimitModeKind), and a new PhaseSPC class as shown below. Tag values updated for the new classes. The changes made above are based on the proposed changes Larry made in the <<CL-7 3 Phase DNP Map Points - OpenFMB-Profiles-20201118a>> spreadsheet | [12 empty] | Closed
86 | Larry | 2020-09-28 |  | Data Model |  | Issue raised by Larry on some fields such as ENG_ScheduleParameter that has FLOAT32 fields. • Changed ENG_ScheduleParameter 'value' field datatype from FLOAT32 to FLOAT64 • Both ControlDPC and ControlSPC have the same Boolean field but StatusDPS and StatusSPS are different. The StatusSPS returns a Boolean value but StatusDPS can have a value such as transient. | [12 empty] | Closed
85 | Larry & Cory | 2020-09-25 |  | Data Model |  | Issue raised by Larry & Cory on why “i” is in the AnalogueValue class if not in use and an uncontrollable field. • AnalogueValue & AnalogueValueCtl issue (attribute “i” not in use) o Added a new data type class, FLOAT64, following the existing pattern. The FLOAT64 is basically a “double”. o Two classes (Vector & MV) with attributes pointing to the AnalogueValue are re-casted to FLOAT64 o Two classes (ASG & ControlAPC) with attributes pointing to the AnalogueValueCtl are recasted to FLOAT64 o Both AnalogueValue & AnalogueValueCtl are removed from the OpenFMB model • A new optional field, isUncontrollable, is added into the LoadStatus class. ProtobufTag value updated. | [12 empty] | Closed
84 | Dwayne, Larry, and Shawn | 2020-09-17 |  | Data Model |  | • IED removed o Relevant ProtobufTag renumbered • q, t changed to optional for the following 2 classes: o ENS_DERGeneratorStateKind o VSS • Model renamed to “OpenFMB Operational Model (61850-CIM) (v2.0.0).eap” | [2024-10-30]: This issue list has not been updated since 2021 during the major model update for the Grid Codes. A number of issues had been only logged in Shawn's notes document. It is decided that these issues should be added back to this issue list and then the new issues can be added for discussion/approval following the standard procedure. So the items added above this row are afterfact issues for documentation only. | [11 empty] | Closed
83 | Shawn H. | 2021-08-13 |  | Data Model |  | Added GenerationCapabilityProfile diagram with the following new classes: - GenerationCapabilityProfile - CapabilityMessageInfo - GenerationCapability - GenerationCapabilityDGEN - CapabilityValue - CapabilityDGEN | [12 empty] | Closed
82 | Jed (SEL) | 2020-08-19 |  | Data Model |  | Need to compliant with IEEE1547 for the DER profiles See previous issue item #77 |  | [2024-11-25] Check the old version v11 data type and find what was deleted | [9 empty] | Gateway | Open
81 | Brian/Jed (SEL) | 2020-04-15 |  | Data Model |  | Data model gaps: - Group setting - Capacity (see Item #65) - Need to simultaneously open/close 5 reclosers and deal with what if scenario such as 4 open but 1 not (command/operation status) | [2020-04-15]: Jed proposed to work on use case (Activity Diagram) to start with. Jed may have some activity diagrams ready for review in 2 weeks. | [2020-06-17]: - Contact Dmitry for the nameplate information [2020-07-09]: Work session (Dwayne, Larry, Jed, Bryan, and Shawn) [2020-07-15]: Work session (Dwayne, Larry, Cory, Shawn) Protection mode such as a group setting or pre-defined curve profile. It is usually pre-defined by a circuit segment service. [2020-07-22]: Dmitry recommeded to use the existing protection related LN classes. Dmitry will share the information with the team. [2020-08-05]: Issue closed (after adding the ACD class from 61850) | [9 empty] | Gateway | Closed
80 | Larry | 2020-04-15 |  | Data Model |  | To prioritize data model profiles |  | [2020-04-22]: Done | [10 empty] | Closed
79 | Stuart L. | 2020-04-08 |  | Use Case |  | Proposed to have a FLISR use case session | [2020-04-15]: Brian/Jed from SEL presented the use case | Done See Issue #81 | [10 empty] | Closed
78 | Dwayne | 2020-04-06 |  | Data Model |  | Need to add weather data profile | See CIM17v23 Environmental model | [10 empty] | Operational | Open
77 | Jed | 2020-04-01 |  | Data Model |  | I had some notes on pouring through the model. I'll try to formulate it better by our next meeting, but there is a capability notice in the status (or if we add boilerplate profiles), about what modes of internal regulation a generation/solar/ess will support, and then also a control and status for what control mode it is in. Generators can, broadly speaking, have a control loop for regulating. Their real power output. These can be: Droop (Allows a setpoint of slope and y-axis intercept) ISO (Allows a setpoint of target frequency) Power (Allows a setpoint of real power) The voltage loops have correlaries: VarDroop (Allows a setpoint of slope and y-axis intercept) Voltage Regulation (Allows a setpoint of terminal voltage, need to specify where the measurement point is - high-side of transformer/POI) VAR (Allows a setpoint of reactive power). These are in addition to the particular setpoints for 1547, and have some interactions with them.Not all generators / ess / solar units can support all modes, and any microgrid controller will need to understand their controlled unit's capabilities and be able to set these parameters in order to perform Generation Control System (GCS) use-cases -- which is the Use-Case driver that we're missing at the moment that would drive these parameters. | [2020-04-08]: Reviewed a proposed GenerationControlProfile model. The team decided to wait for late until the FLISR use case is discussed (See new Issue #79) [2020-06-17]: Half of the issue has been covered by the ReserveRequest/ReserveAvailability profiles. The other half is about the generation control - GCM use case - need meetings (for both use case and data modeling sessions). | [2020-07-16]: Work session (Dwayne, Larry, Curt, Jed, Bryan, Shawn) Updated the GenerationDiscreteControl profile [2020-07-22]: Dmitry: there are classes in 61850-7-420 (ed.2) Bryan: SEL will be looking into the standard [2020-08-05]: Jed to look into the standard (ed 1 if ed 2 not released) Jed to provide a name for the VV11PlaceHolder class in the GenerationDiscreteControl profile [2020-08-12]: Jed proposed a solution with a VV11 class. Dmitry recommended using 61850 LN class. Offline meeting is needed [2020-08-18]: Work session with Jed, Dmitry, Larry, Dwayne, Shawn • Delete the V11 data type class in the GenerationDiscreteControlProfile. The compliance to IEEE 1547 will be addressed after v2.0 [2020-08-19]: Closed and added a new issue (#84) | [9 empty] | Gateway | Closed
76 | Larry & Stuart | 2020-03-25 |  | Data Model |  | Need to add more profiles into Meter module such as discrete control and event/status. Currently there is only one reading profile in the module. | [2020-06-17]: Stuart L. to follow up with vendor for requirements | [2020-04-22] Offline meeting needed [2020-07-22]: Waiting for requirements [2020-08-19]: Decided to only keep the reading profile for now. | [9 empty] | Gateway | Closed
75 | Jed | 2020-03-18 |  | Data Model |  | Apply to all modules: [From Jed]: OpenFMB needs to decide how to deal with quality of data. Embedding the quality or "IEDTrouble" inside the message is not viable, because if there is trouble, the receiving application cannot count on the device properly forming messages anymore. Instead, I propose a pre-defined publishing schedule, and that a number of missed messages indicates failure. This means that devices would be tested to cease publication if they have an internal diagnostic failure, and provides a single thought-through, robust failure-detection mechanism for subscribing applications. | [11 empty] | Management Service | Open
74 | Jed | 2020-03-17 |  | Data Model |  | Handling Revisions/Derivatives (UML changes / extensions) | Proposed: - Version control EA file as a stand alone file (note a UML model is a living model, official release is key) - Centralize the EA file such as on Basecamp - Participants who like to add extensions, should download the latest version as a snapshot version - Model manager (gatekeeper) and team to review and merge as needed. - EA Protobuf generator source code for maintaining | [2020-04-01]: Jed is testing some EA approaches, use case related. [2020-04-08]: Jed demonstrated GitLab for model update and versioning [2024-11-25]: Refer to #162 | [9 empty] | Other | Closed
73 | Data Modeling Team | 2020-03-11 |  | Data Module |  | Need a new data module for the Sky Camera |  | [2020-04-01]: Hold for now [2020-06-17]: Not needed anymore | [9 empty] | Gateway | Closed
72 | Data Modeling Team | 2020-03-11 |  | Actor |  | Review current actors in the fundational use cases. Discuss the optimizer. | Proposed: - Electrical State Service - Electrical Connectivity Service - Market Service - Load Forecast Service - Weather Forecast Service | [2020-04-01]: Hold for now [2024-11-13]: Chirath will review the use cases (related to #160) | [9 empty] | Operational | Open
71 | Data Modeling Team | 2020-03-11 |  | shuntmodule |  | Rename the shuntmodule to capbankmodule | [2020-04-23]: Shawn: - Model updated with the following questions: o CapBankEventAndStatusYPSH/ShOpCap rename & notes change? ([2020-05-01]: change to OpCap) o Should the capability part moved to a separate profile? ([2020-05-01]: Keep it for now) o Ok to change proto tag value? | [2020-04-01]: Agreed. [2020-06-17]: Double check [2020-06-24]: Status changed to Closed [2020-07-01]: Reviewed with the team on 07/01, no objection. [2020-07-15]: Not change ShOpCap name to better align with 61850 | [9 empty] | Gateway | Closed
70 | Data Modeling Team | 2020-03-10 |  | EV & EVSE |  | May need new profiles for EV (BTM, V2G) |  | [2020-04-01]: Duke has the need to include these profiles. No data requirements at the moment. Hold for now. Dmitry: 61850-90-8 [2024-11-25]: Curtis will review the documents | [9 empty] | Operational | Open
69 | Data Modeling Team | 2020-03-10 |  | DER Curve |  | Need different group function curves at different time point. Jerry Gray from EPRI may have the use case. | [2020-03-10] Briefly discussed using the CIM Curve/CurveData that was in Phase 1 & 2 OpenFMB model | [2020-04-01]: Need more requirements to decide the next step. Jim/Dmitry LN: FCSD In the current SolarControlProfile, FSCH is in use which is for scheduling only. It is probably better to use FCSD (generic curve for multiple uses) See Issue #77 [2020-07-22]: Issue closed | [9 empty] | Gateway | Closed
68 | OpenFMB Meeting (Jed) | 2020-03-10 |  | Safety Profile |  | Safety model - direct control mode Hotline tag and etc. Either new profile or <..>Status (recloser, generator, switch, breaker) | Need more information [2020-03-10] May be covered by the DeviceStatus (see Issue #63) | [2020-03-25]: Add into the existing <..>Status profiles Need to revisit the DeviceStatus class. Is there a 61850 LN? Offline meeting needed [Dmitry]: [2020-04-22]: Offline meeting needed. Need 61850 support. [2020-06-10]: • Reset data model (Larry, Dwayne, and Cory) o Added “reset” and “iedTrouble” into ControlValue o Merged and removed a couple of fields from DeviceControl class [2020-06-17]: Reviewed (BreakerDiscreteControl profile) with the team. Not completed [2020-06-22] (Larry, Bryan, Dwayne, Shawn) • Added the HotLineTag (type of PPS) and RemoteBlk into the LogicalNodeForEventAndStatus [2020-06-24]: AI: Larry to check with Cory / Dwayne on if "reset" field is needed in the status and event profiles. [2020-07-01]: Reviewed in the 07/01 team meeting, no objection on the two fields (HotLineTag & RemoteBlk) in the LogicalNodeForEventAndStatus | [9 empty] | Gateway | Closed
67 | Dwayne | 2019-12-11 |  | MV & CMV |  | May need to change the q and t in the MV and CMV classes as optional fields, rather than required as currently defined based on the original 61850 model | [2020-03-10] Need to talk to the team first. | [2020-03-25]: Team agreed to make the two fields optional [2020-03-26]: t and q changed to optional in both CMV and MV [2020-04-01]: Reviewed with the team and decided to close the case. | [10 empty] | Closed
66 | Dwayne | 2019-11-15 |  | Protobuf Tag |  | Found an issue with protobuf tags - some of the existing tags from the previously released model were changed in BreakerStatusProfile, RecloserStatusProfile and SwitchStatusProfile with the addition of the "DeviceControl" class - we must make sure that no existing tags are EVER changed going forward as it breaks backwards compatibility with existing code - this is something that I should have caught previously before committing the code | Dwayne updated the model and uploaded to the Basecamp site | [11 empty] | Closed
65 | Dwayne | 2019-11-11 |  | Capabilities Profiles |  | Make sure that we add "capabilities" profiles to our list of items that we need to addressed for OpenFMB. We really need the ability of having devices publish their "capabilities" so subscribers and determine how to manage them. This would eliminate the necessity of storing this information in some central system that every application would need access to. For instance, an ESS need to be able to publish that it is rated for 625kW/326kWh so that subscribers can know what energy and power is truly available when the ESS publishes its status saying that is is 78% SOC. We really should have this information available from every device module in OpenFMB. | [Shawn]: CIM AssetInfo (nameplate) vs. OpInfo [2020-03-10 OpenFMB meeting]: Look into SEP2 (IEEE2030.5) capability model Low priority for now (meeting with Larry and Dwayne). Need support from 61850 [SH]: Reviewed 61850-7-420: LN DWGC, DWMX and DWMN (see Figure 95) for Active Power functions. [2020-03-18] Dmitry Already requested in the 61850 community | [2020-04-22]: Add new profiles into the existing modules for capability models [2020-06-17]: Meetings needed [2020-07-22]: Waiting for requirements Dmitry: look into 7-420 [2020-08-05]: Hold for now (Dwayne and Larry discussed on 08/04/2020) | [9 empty] | Gateway | Deferred
64 | Dwayne | 2019-11-05 |  | Switch Status |  | Updates from Dwayne: Removed spaces in SwitchingCapabilityKind enum Change relationship for DeviceControl in BreakerDiscreteControlProfile, RecloserDiscreteControlProfile and SwitchDiscreteControlProfile - was 0..* - changed to 0..1 ShuntEventProfile now inherits from EventMessageInfo - was inheriting from StatusMessageInfo | [12 empty] | Closed
63 | Dwayne, Bryan F, Shawn | 2019-10-21 |  | Switch Status |  | The list in the "6 SEL B - Fazzari" presentation needs to be included in the 3 profile (Switch/Recloser/BreakerStatusPorfile) except the followings: 1) The first 2 already in the Measurement profile – no change 2) 52A is a combination of 51a and 52a which have been covered by the current Switch (Breaker/Recloser)Status. Dps 3) The following 3 do not need to be included: a. Inhibited b. Bypassed c. Out of service All listed for the Status profiles should be also included into the corresponding ControlProfiles excep: 1) Recloser Enabled (or Remote control) 2) Use SPC (Boolean) for all fields | [2020-03-10] Need to revisit the DeviceStatus fields in the SwitchStatus diagram (where they belong especially where they are in 61850 LN) [2020-03-18] Jed Regarding 3) - missing status IEDTrouble revisit | See Issue #81 | [10 empty] | Closed
62 | Dwayne | 2019-10-21 |  | Data type |  | Add either "nanos" or "nanoseconds" to the commonmodule.Timestamp definition - UINT64 o "fractional" seconds is a concept that most folks have no idea how to handle and I'm seeing people interpret that wrong and set the field incorrectly o application developers will better understand nanoseconds and I think it will benefit end users eventually o "people" can grasp "milliseconds," "microseconds" or "nanmoseconds" way easier than "fractional seconds" | [2020-03-10]: Drop fraction and add nanosecond (INT32U) in the Timestamp Note the protobuf tag should not be reused. [2020-03-18]: Further discussion. Need Dwayne on the call. | [2020-03-25]: Team decided to add nanosecond to replace fraction in the timestamp class (note the protobuf tag numbering) [2020-03-26]: Updated both TimeStamp and ControlTimeStamp to add "nanoseconds" field (ProtobufTag=4) and added ProtobufTag_Reserved (value=1 since the deleted fraction tag was 1) for the 2 classes. The original "fraction" field (ProtobufTag=1) is deleted. [2020-04-01]: Reviewed with the team and decided to close the case. Dwayne will provide sample data for clarification. | [10 empty] | Closed
61 | Larry | 2019-09-24 |  | Slide deck |  | Change the OpenFMB data model process diagram to align with the update in the NAESB document | The one posted on Slack is a PDF hence emailed the updated slide to Larry for uploading on 10/15/2019 | [11 empty] | Closed
60 | Dwayne | 2019-09-24 |  | Per-phase status/event/control info |  | We are missing per-phase status/event/control info for several of the modules: - Breaker - Recloser - Regulator - Shunt (cap bank) - Switch - and any module as needed | [2020-03-18] Dmitry 61850-7-4 (-7-3) Ed2.1 / UML available 61850-7-420 (DER) Ed.2 will be released soon May review all the module to see if a migration to 61850 Ed2.1 LN is needed. Contact Herb | [2020-06-22] (Larry, Bryan, Dwayne, Shawn) • New CDC, PPS (Per Phase Status) • Merged the fields in the DeviceStatus o Added FaultLatch into the StatusAndEventXSWI o Added FaultLatch, RecloseLockout and RecloseEnabled into the StatusAndEvetXCBR o See breakerstatusprofile and switchstatusprofile [2020-06-24]: Offline meeting needed for the per-phase control. [2020-07-01]: Reveiwed in the 07/01 meeting, no objection [2020-12-14]: Updated Regulator and CapBank profiles (detail provided in the meeting on 12/16/2020. [2020-12-16]: Newly updates reviewed by the team. 2) Jed has a concern on secondaryReadingMMXU in both CapBank and Regulator reading profiles. The concern is that the OpenFMB is usually used for the primary side, if only secondary reading is provided, it could be a problem since no ratio is provided and as a result primary side reading cannot be extrapolated. One proposal is to set the current “readingMMXU” as required. Team decided to discuss this further in 2021. This may be covered by updating the test case scenario with a rule that when a secondaryReading is populated, the primary readingMMXU has to be populated. | [9 empty] | Gateway | Closed
59 | Dwayne | 2019-09-24 |  | shuntmodule |  | Cap banks are going to be needed as a component of managing Volt-Var in many utilities | Review the previous OpenFMB data model released back in 2016. We had a "shuntmodule" in that model but it wasn't utilized. We are potentially going to need the following profiles: 1) ShuntReadingProfile 2) ShuntStatusProfile 3) ShuntEventProfile 4) ShuntControlProfile 5) ShuntDiscreteControlProfile (maybe) We should be able to pull "reading" profile from other modules. Need to determine which 61850 LN's are relevant for status/event/control. | [2020-03-10] Need to be reviewed by the group in the data modeling meeting. See Issue #71 | [10 empty] | Closed
58 | Dwayne | 2019-04-24 |  | Data Model |  | In each of our packages under "OpenFMB Information Model", we put the following "tag": ProtobufTag_go_package We need to update the "root" of the value in this tag in each of the packages as follows: Old: github.com/mthollylab/go-openfmb-protobuf/ New: gitlab.com/openfmb/psm/ops/protobuf/go-openfmb-ops-protobuf/ For instance, in the "metermodule" package, the value for ProtobufTag_go_package would now be: Old: github.com/mthollylab/go-openfmb-protobuf/openfmb/metermodule New: gitlab.com/openfmb/psm/ops/protobuf/go-openfmb-ops-protobuf/openfmb/metermodule | [From Dwayne]: To rename the model file to something like this: OpenFMB Operational Model (61850-CIM).eap The reasons for this change are: • The data models that are in this particular UML are for "operational" (i.e. OT) use cases. Over time, more device and "application" models will be added but they should be ones targeted for OT use cases. • There will be new models in the future for things like "management services" ("OpenFMB Management Services Model.eap" perhaps?) that should probably stay separate to keep the models from growing out of control and keep them focused. • Once we load the model to GitLab, the date as part of the file name will not be needed. We will be "tagging" the model file with "release" tags to indicate the proper versions going forward. I do NOT think that you need to change the namespace dates in the model as they have not changed since last November. | [11 empty] | Closed
57 | Larry | 2019-04-11 |  | NAESB figures |  | [See Larry's email on 4/11/2019]: As noted in your NAESB R19003 Request, three updated diagrams need to be submitted: Replacement for Figure 6.3-1: OpenFMB Data Modeling Approach Replacement for Figure 6.3-2: Sample Data Profile Replacement for Figure 6.3-3: Sample Module Organization | [12 empty] | Closed
56 | Dwayne | 2019-04-05 |  | Data Model |  | For use at more locations option go_package should probably change from: option go_package = "github.com/mthollylab/go-openfmb-protobuf/openfmb/essmodule"; to the more generic: option go_package = "github.com/openfmb/go-openfmb-protobuf/openfmb/essmodule"; | Don't change anything yet. 😁 Once we finalize the repository, we'll make the change for the model. | See newer issue #58 | [10 empty] | Closed
55 | Shawn H. | 2019-02-27 |  | LN |  | Just an FYI, based on the update by Andre Maizner in the IEC CIM meeting in Charlotte, the "mRID" has been added into the 61850 LogicalNode class. As a result, the OpenFMB may be updated if there is another revision. Currently the LogicalNode is inherited from the CIM IdentifiedObject which contains mRID already. |  | [2020-04-22]: No change | [10 empty] | Closed
54 | Dwayne | 2019-02-21 |  | Protobuf tag |  | Need a protobuf tag to indicate which class can be defined as a message similar to the DDS nested tag. This will prevent from publishing classes that do not meant for message. | Added 2 things per request from Dwayne: 1) Top message level class "MessageOptions with an attribute "option_openfmb_profile:boolean=51000 2) Add a tag, ProtobufTag_openfmb_profile=TRUE, for all <..>Profile classes | [11 empty] | Closed
53 | Larry | 2018-10-10 |  | ConductingEquipment |  | ConductingEquipment is used mainly for an asset presentation in OpenFMB. This deviates a bit from the original CIM model | Need to talk to ABB team about the DSE topology model. | Description changed that the ConductingEquipment is an asset view rather than a true conducting equipment logical view since at Duke, there is no logical connection point ID. The classes such as Breaker all populated with an asset serial number. In the future when the connection point ID is available, for example from GIS system, then the population of the data will be changed to use the connection ID rather than the asset ID. No model change is needed. | [10 empty] | Closed
52 | Larry | 2018-10-08 |  | Resource model |  | 1) Create a Meter Module and MeterReadingProfile Copy the existing ResourceReadingProfile into the Meter Module, making a MeterReadingProfile - who would have thought! Change the name of the ResourceReadingProfile class to MeterReadingProfile Change the name of the ResourceReading class to MeterReading class 2) In the existing ResourceReading Profile Change the name of the Meter class to PowerSystemResource class 3) In the existing ResourceStatusProfile Add a PowerSystemResource class between the ResourceStatusProfile and ConductingEquipment | 1) Created a new profile for the MeterReadingProfile 2) & 3) Simply remove the Meter class since ConductingEquipment is a type of PowerSystemResource already | [11 empty] | Closed
51 | Dwayne | 2018-10-02 |  | Data model |  | Change "xVal" in all of our specialized "xxxPoint" classes to "startTime" like we have in the generic SchedulePoint class | Change for the following classes: - ESSPoint and ESSPointStatus - Generation Point and GenerationPointStatus - InterconnectionPoint - LoadPoint and LoadPointStatus - SwitchPoint (Recloser and Switch controls) - RegulatorPoint and RegulatorPointStatus - SolarPoint and SolarPointStatus | [11 empty] | Closed
50 | Larry | 2018-10-02 |  | Data model |  | [From Larry]: Delete ESSFunctionKind, ESSFunctionParameterKind, and the matching attributes. Create the following classes: Class CapacityFirming capacityFirming: boolean limitPositive_dp_dt: FLOAT32 limitNegative_dp_dt: FLOAT32 Class FrequencyRegulation frequencyRegulation: boolean frequencySetPoint: FLOAT32 frequencyDeadBandPlus: FLOAT32 frequencyDeadBandMinus: FLOAT32 overFrequencyDroop: FLOAT32 underFrequencyDroop: FLOAT32 gridFrequencyStableBandPlus: FLOAT32 gridFrequencyStableBandMinus: FLOAT32 Class PeakShaving peakShaving: boolean pealShavingLimit: FLOAT32 baseShavingLimit: FLOAT32 socManagementAllowedHighLimit: FLOAT32 socManagementAllowedLowLimit: FLOAT32 Class SocLimit socLimit: boolean socHighLimit: FLOAT32 socLowLimit: FLOAT32 socHighLimitHyteresis: FLOAT32 socLowLimitHyteresis: FLOAT32 Class SOCManagement socManagement: boolean socSetPoint: FLOAT32 socDeadBandPlus: FLOAT32 socDeadBandMinus: FLOAT32 socPowerSetPoint: FLOAT32 Class VoltageRegulation voltageSetPoint: FLOAT32 voltageDeadBandPlus: FLOAT32 voltageDeadBandMinus: FLOAT32 overVoltageDroop: FLOAT32 underVoltageDroop: FLOAT32 Class VoltageDroop voltageDroop: Boolean voltageRegulation: VoltageRegulation Class VoltagePI voltagePI: boolean voltageRegulation: VoltageRegulation Class ESSFunction capacityFirming: CapacityFirming frequencyRegulation: FrequencyRegulation peakShaving: PeakShaving socLimit: SocLimit socManagement: SOCManagement voltageDroop: VoltageDroop voltagePI: VoltagePI | [12 empty] | Closed
49 | Larry | 2018-09-29 |  | Notes |  | The attribute specific note for seconds and for fraction make sense. What I didn't understand was the white note on the ResourceReadingProfile that talks about 24 bits for the fraction of a second and 8 bits for time quality. It seemed as though that white note on the diagram could be removed. | Agreed to remove the notes that attached to Timestamp in the ResourceReadingProfile diagram | [11 empty] | Closed
48 | Lorenzo | 2018-09-28 |  | Data Type |  | • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'value' with Attribute Type 'int' in Element 'ENG_ESSFunctionParameter'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'sequenceNumber' with Attribute Type 'int' in Element 'ACDCTerminal'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'value' with Attribute Type 'float' in Element 'ActivePower'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'positiveRealPowerKWPerMin' with Attribute Type 'float' in Element 'RampRate'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'negativeRealPowerKWPerMin' with Attribute Type 'float' in Element 'RampRate'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'positiveReactivePowerKVArPerMin' with Attribute Type 'float' in Element 'RampRate'. • ERROR - Main.ProcessElementAttributes - Invalid data type in Open FMB Model for Attribute Name 'negativeReactivePowerKVArPerMin' with Attribute Type 'float' in Element 'RampRate'. | 1. The class INT32 has a UML data type of “int” and that UML data type of “int” is replaced with the Protobuf data type of “int32”. The Data Type Wrapper may replace the “int32” with “Int32Value”. 2. The class FLOAT32 has a UML data type of type of “float” and there is no further replacement because the UML data type of “float” is the same as the Protobuf data type. The Data Type Wrapper may replace the “float” with “FloatValue”. | [11 empty] | Closed
47 | Lorenzo | 2018-09-27 |  | Data Type |  | 1. ERROR - Proto3Field.determineProtobufDataType - Invalid data type in Open FMB Model for Attribute Name 'option_multiplicity_min' with Attribute Type 'int' in Element 'FieldOptions'. 2. ERROR - Proto3Field.determineProtobufDataType - Invalid data type in Open FMB Model for Attribute Name 'option_multiplicity_max' with Attribute Type 'int' in Element 'FieldOptions'. 3. ERROR - Proto3Field.determineProtobufDataType - Invalid data type in Open FMB Model for Attribute Name 'ctlVal' with Attribute Type 'INT8' in Element 'ControlISC'. 4. ERROR - Proto3Field.determineProtobufDataType - Invalid data type in Open FMB Model for Attribute Name 'stVal' with Attribute Type 'ObjRef' in Element 'ORS'. 5. ERROR - Proto3Field.determineProtobufDataType - Invalid data type in Open FMB Model for Attribute Name 'stVal' with Attribute Type 'INT8' in Element 'StatusISC'. | [Proposal from Larry]: For items 1, 2, 3, and 5 I'd suggest changing int/INT8 to INT32 as that is the underlying protobuf representation anyway, and we can't enforce restrictions. For item 4, I don't understand how ObjRef is used. Could you clarify? Also, I'm not clear about this note in the ResourceReadingProfile: | [11 empty] | Closed
46 | Larry | 2018-08-31 |  | Data Model |  | VisString255 Unicode255 are deadwood that are no longer being referenced now that we cleaned-up schedules. | VisString255 is not an orphan in the model. It is still in used by the following two classes: - ENS_HealthKind - VSS UniCode255, on the other hand, can be removed. | Decided to change the data type to "string" for the two fields (See Larry & Adam's email on 09/02/2018) and then delete the VisString255 [From Larry]: Primarily what is driving my questions is that each Simple Type we add requires writing special handling code for Protocol Buffers and the like. Think of the primitive type table Lorenzo showed us; and there is an equivalent in the adapter. We do that for the numeric types because of the major differences in their behavior and accuracy, differences which slightly longer or shorter strings don't have. Others may have thoughts about the benefit for the effort and ongoing extra maintenance. [From Adam]: Constraints don't add any value unless the run-time representations (e.g. protobuf / DDS) can enforce them. Protobuf cannot express string constraints. It *can* express limited integer constraints via signed/unsigned and 32/64 bit lengths. All I see is extra complexity w/ the additional string types w/o any realized value. | [10 empty] | Closed
45 | Larry | 2018-08-30 |  | Data Model |  | Need to change the ControlScheduleFSCG structure to accommodate more values (see the ScheduleStructureProposal Word document from Larry) | Updated. See the 2018-08-30 version. | [11 empty] | Closed
44 | Larry | 2018-08-15 |  | Data Model |  | The Optimizer module doesn't seem to fully follow our current patterns (See Interconnection and Coordination service modules) and appears to need both our xxxMessageInfo IdentifiedObject and ApplicationSystem NamedObject | [12 empty] | Closed
43 | Larry | 2018-08-01 |  | Data Model |  | Key: ==== mRID in ConductingEquipment is currently marked with the DDS key tag. The same field also needs special treatment for other publish - subscribe protocols. So, could we please add to it a new tag: ProtobufTag_Key true and the corresponding option number: option_key:boolean = 50005 ESSControlProfile: ============== In ESSPoint could we change functionParameter to functionParameters as there are several parameters associated with each function: and in ENG_ESSFunctionParameter change name to functionParameter as name is normally a string elsewhere: | Key updated as requested ESSPoint.functionParameter need confirmation from Larry (email on 08/01/2018): The plural name used for single XSD instance may need some discussion here. Larry's reply: Agreed, that the XML serialization looks unusual with the "s" so could we: • Keep the existing functionParameter • Change the "name" of each parameter to "functionParameterKind" | [11 empty] | Closed
42 | Larry | 2018-06-12 |  | Data Model |  | In: ENG_GridConnectModeKind ENG_ESSFunctionKind ENG_CoordinationServiceModeKind setValExtension has a multiplicity of 1 such as shown below when Dwayne and I believe setValExtension should be optional since it is only be used when a kind of "other" has been selected. | Change as recommended | [11 empty] | Closed
41 | Larry | 2018-06-06 |  | ControlTimestamp |  | So for in the body of Controls where the date/time is in the future (not in ControlMessageInfo), it would be comparable to have: ControlTimestamp fraction: INT32U seconds: INT64U This would impact all Control Profiles but only xVal of SchedulePoint and other cases of xVal Timestamp in such as: GenerationPoint ESSSchedulePoint LoadPoint SolarPoint SwitchPoint | Replace Timestamp with ControlTimestamp (no tq) for the followings: SchedulePoint GenerationPoint ESSPoint LoadPoint SolarPoint SwitchPoint | [11 empty] | Closed
40 | Larry | 2018-06-06 |  | ESSPoint |  | It seems like: functionParameter: ENG_ESSFunctionParameter [0..1] should be: functionParameter: ENG_ESSFunctionParameter [0..*] | Change as recommended | [11 empty] | Closed
39 | Larry | 2018-06-05 |  | SwitchCSG |  | SwitchCSG still has xUnit but with the recent change to the profile and to be consistent with other controls with x as a timestamp, the xUnit in SwtichCSG is no longer needed. As an optional field it doesn't interfere with anything now, but could you please remove it when we next do an update. | Change as recommended | [11 empty] | Closed
38 | Larry | 2018-05-31 |  | SolarEventProfile SolarStatusProfile |  | Remove the SolarStateKind and its relavent classes and attributes such as the ENS_SolarStateKind | Change as recommended | [11 empty] | Closed
37 | Larry | 2018-05-31 |  | SolarControlProfile & GenerationControlProfile |  | It appears that the SolarControlProfile and GenerationControlProfile still have a field that has been replaced. For the SolarControlProfile the singular SolarControlMod has been replaced by state in the SolarPoint schedule, so the required SolarControlMod looks like it should be removed. For the GenerationControlProfile the singular GnCtl has also been replaced by state in the GenerationPoint schedule, so GnCtl looks like it should be removed. | Change as recommended ENC_SolarControlKind removed as a result | [11 empty] | Closed
36 | Larry | 2018-05-23 |  | RecloserControlProfile |  | In the RecloserControlProfile while SchedulePoint has an xVal Timestamp, it needs a ControlDPC like the switch SwitchPoint/SwitchCSG. | Change as recommended | [11 empty] | Closed
35 | Larry | 2018-05-23 |  | SwitchControlProfile |  | In the SwitchControlProfile the x axis of SwitchPoint should be time with xVal as a Timestamp instead of FLOAT32 | Change as recommended | [11 empty] | Closed
34 | Larry | 2018-05-14 |  | Vresioning for UML, XSD, IDL, Proto |  | [From Larry 5/14/2018]: IDL includes at the top of the output the: source UML file date/time of IDL generation Its all automatic with no manual version specification. Andre, looks like you could be off the hook. 😉 Proto Lorenzo, could you do the same as with the IDL? In addition, there are some minor related questons a) This definition is utility specific package commonmodule // import "github.com/mthollylab/go-openfmb-protobuf/openfmb/commonmodule" Generically "mthollylab" should probably become "openfmb" but does suggest there utility-specific UML, IDL, Protos, etc. are likely b) The protos has been as separate files in a zip file, but protoc generates the output in XXXmodule/XXXpb.go. Is this intended? UML Shawn, a) Currently we specify a version by the name of the ea file, which seems to have worked for several years and eliminates the potential issue of an out-of-date version tag in the ea file. 😉 b) How do we handle multiple utilities? Import/export packages? Adapter Plugins and Adapter a) adapter plugins may need to carry though the UML, IDL, and / or Proto source file name and time of generation from the comments near the top of the .idl or .proto And also supply their own x.y.z.build version b) as does the Adapter framework. | Needs UML version, tool version and artifacts version. The version on the wire ia the key. Two separate issues: 1) Traceability (tool version, UML version and artifacts version) 2) Syntax level version (backward compatibility issue) | [2020-04-22]: See Issue #71 | [10 empty] | Closed
33 | Larry | 2018-05-10 |  | Asset Health |  | Larry called Herb who recommended using the ENS_HealthKind | Model updated based on Herb's recommendation | [11 empty] | Closed
32 | Adam & Dwayne | 2018-05-10 |  | Multiplicity |  | Need to define explicit association for terminal reading | Keep as is | No change | [10 empty] | Closed
31 | Lorenzo | 2018-05-09 |  | Package tag |  | Openfmb header protobuf tags at wrong place after the package structure was rearranged | [12 empty] | Closed
30 | Larry, Dwayne | 2018-04-27 |  | Traceability in the model |  | Need to merge the current data model back to the Phase II business models. Most likely just profile name change. Testing needs to catch up the Phase II use cases. | Shawn to merge the model and do the name change as needed. During the summer, there may be some use case update coming | [11 empty] | Closed
29 | Dwayne | 2018-04-11 |  | Data model |  | Things that we need to do: • Move NamedObject from switchmodule to commonmodule. • Move ApplicationSystem from interconnectionmodule to commonmodule. • In coordinationservicemodule, add the ApplicationSystem object to all of these profiles like we did for the profiles in interconnectionmodule. • Replicate the profile changes from switchmodule to the rest of the “device” modules. Now we have one more change: • In the profiles for both coordinationservicemodule and interconnectionmodule, remove IED from all of these profiles. Since these profiles are really for “applications”, the concept of an IED here doesn’t really make sense. We didn’t really even think about that until we added the ApplicationSystem class to these profiles. | [12 empty] | Closed
28 | Dwayne, Adam | 2018-04-09 |  | Data model |  | Consider to merge all <..>MessageInfo | Issue with the DDS key tag, control profile is different from the reading and status profiles | [11 empty] | Closed
27 | Dwayne, Adam | 2018-04-09 |  | Data model |  | DDS key field shows in two fields in the <..>Control profiles | Remove one DDS key tag | [11 empty] | Closed
26 | larry | 2018-04-03 |  | Data model |  | Change ResourceReading multiplicity from 1..* to 1. | [12 empty] | Closed
25 | Larry | 2018-03-07 |  | Data model |  | Remove LoadEventAndStatusZGLD from ESS Event and Status profiles since it is not needed | [12 empty] | Closed
24 | Dwayne | 2018-03-02 |  | Protobuf descriptor extension |  | Need the following defined in the UML model: package uml; option go_package = "github.com/mthollylab/go-openfmb-protobuf/openfmb"; option java_package = "openfmb"; option java_multiple_files = true; option csharp_namespace = "openfmb"; import "google/protobuf/descriptor.proto"; extend google.protobuf.FieldOptions { bool option_parent_message = 50000; bool option_required_field = 50001; int32 option_multiplicity_min = 50002; int32 option_multiplicity_max = 50003; bool option_uuid = 50004; } | options directly under package are defined as tag values of the /openfmb model view the ones under import statement are modeled in a class (tagged as ProtobufTag_extend=true) directly under the /openfmb view | [11 empty] | Closed
23 | Data Model Team Meeting | 2018-02-19 |  | Data Model |  | CSG xVal is type of FLOAT32, which should be changed to TIMESTAMP | Change xVal unit to TIMESTAMP and remove the xUnit (see ESSControlProfile). Rename CSG to ScheduleCSG class to remove the xUnit which is default to TIMESTAMP. Also update the ESSCSG to remove the xUnit | [11 empty] | Closed
22 | Larry L. / Data Model Team Meeting | 2018-02-05 |  | Model |  | Need a sync state in ESSEventProfile: - Updated ENC_GridControlModeKind - Updated EssEventZBAT - Updated InverterEventAndStatusZGEN | [12 empty] | Closed
21 | Protobuf Team | 2018-01-31 |  | Protobuf |  | New Tags: - ProtobufTag_go_package - ProtobufTag_java_package - ProtobufTag_java_multiple_files - ProtobufTag_csharp_namespace | package breakermodule; option go_package = github.com/mthollylab/go-openfmb-protobuf/openfmb/breakermodule option java_package = openfmb.breakermodule option java_multiple_files = true; option csharp_namespace = "openfmb.breakermodule"; | [11 empty] | Closed
20 | Andre O. | 2018-01-25 |  | Data Model & IDL |  | > /* WARNING: 5 classes could not be generated due to circular > dependencies */ > /* > (<package> , <class>) depends on (<package> , <class>) by means > of <relationship> > ---------------------------------------------------------------------- > ------------ > ( "openfmb::switchmodule::" , "SwitchControl" ) depends on ( > openfmb::switchmodule::" , "SwitchControlFSCC" ) dependency: > aggregation "SwitchControlFSCC" > ( "openfmb::switchmodule::" , "SwitchControlFSCC" ) depends on ( > openfmb::switchmodule::" , "SwitchControlScheduleFSCH" ) dependency: > aggregation "switchControlScheduleFSCH" > ( "openfmb::switchmodule::" , "SwitchControlScheduleFSCH" ) > depends on ( openfmb::switchmodule::" , "SwitchCSG" ) dependency: > attribute "ValDCSG" > ( "openfmb::switchmodule::" , "SwitchCSG" ) depends on ( > openfmb::switchmodule::" , "SwitchCSG" ) dependency: attribute "crvPts" > ( "openfmb::switchmodule::" , "SwitchControlProfile" ) depends on > ( openfmb::switchmodule::" , "SwitchControl" ) dependency: > aggregation "switchControl" | [Dwayne]: The problem is in SwitchCSG. The crvPts field is of type SwitchCSG instead of SwitchPoint. | [11 empty] | Closed
19 | Robby S. | 2018-01-24 |  | Data Model |  | How to model power factor | SunSpec try to harmonize IEEE2030.5 and CIM Robby to provide SunSpec document and IEEE2030.5 | [2020-04-22]: Closed for now. Can be re-opened as needed | [10 empty] | Closed
18 | Dwayne B. | 2018-01-13 |  | Data Type |  | IDL translates long into 32 bit | This seems an issue with the IDL generator. The long should be translated into 64 bit (long long in IDL). The int is 32 bit. Note there is another xsd:integer which is unbounded but can be further restricted | [11 empty] | Closed
17 | Dwayne B. | 2018-01-11 |  | Data Model |  | For “BreakerReadingProfile”, we have a “1..*” relationship to BreakerReading. Should that really be “1..2”? A breaker at most has 2 terminals associated to it, right? I know that we have had this conversation before but I keep forgetting where we landed. For both “SwitchReadingProfile” and “RecloserReadingProfile”, there is no multiplicity to SwitchReading and RecloserReading. Shouldn’t the pattern be the same as the one for BreakerReadingProfile->BreakerReading? | Change BreakerReadingProfile --> BreakerReading target role multiplicity to 1..2 Same applies to SwitchReadingProfile and RecloserReadingProfile | [11 empty] | Closed
16 | Modeling meeting | 2018-01-10 |  | Data Model |  | CSG: xD, yD, and zD as optional fields Specialize CSG as needed | Added SwitchCSG, ESSSCG and etc. What about limit of the arrays | [11 empty] | Closed
15 | Modeling meeting | 2018-01-10 |  | Data Model |  | Add Overview diagram to summarize the modeling rules (NDR) |  | [2020-04-22]: Closed for now. Can be re-opened as needed | [10 empty] | Closed
14 | Modeling meeting | 2018-01-10 |  | Data Model |  | Quality change from bitmap to explict fields similar to Quality61850 | q to follow Quality61850 (or follow the latest -7-2 P_Quality (DetailQual) tq to follow the -7-2 definition (leapSecondsKnown, clockFailure, clockNotSynchronized, timeAccuracy (int8u)) Quality" By referencing information in 7-2, converting our current Quality of a byte[2] type into individual fields in fairly easy. • ValidityKind is simply a new enum with the 4 values from 7-2: 0=good (default), 1=invalid, 2=reserved, 3=questionable. • SourceKind is a new enum with the 2 values from 7-2: 0=process (default), 1=substituted • DetailQual is a new class with 8 boolean fields with "false" as the default: badReference, failure, inaccurate, inconsistent, oldData, oscillatory, outOfRange, overflow • 7-2 indicates that all of these fields are "PresCond"="M" which I'm assuming means "mandatory". But...since all of the fields actually have a default value of either "false" for the boolean values and "0" for the enums, are they really mandatory? If they are really optional, does that make Quality optional in other classes like CMV and MV as well? Right now, Quality is required in those classes. TimeQuality: • New class with 3 boolean fields all marked "mandatory": ClockFailure, ClockNotSynchronized, LeapSecondsKnown. Documentation doesn't indicate what is the default value for these fields. Herb question... • TimeAccuracy - Herb indicated that we might want to skip this field in our OpenFMB data model. Right now, I think that we need to keep it in here somehow. The main reason is if a 61850/OpenFMB adapter/bridge is created in the future (as I expect it will be) with data flowing both to and from both sides, this information shouldn't be lost in the translation. The question now becomes how to implement it. I would like to see this as an enum so we can represent the 61850-5 time performance classes that are listed in Figure 6 of 7-2. I'm currently looking to see if there is a good way of doing that in protobuf. I'll post updates in the comments below as I experiment further. | [11 empty] | Closed
13 | Modeling meeting | 2018-01-10 |  | Data Model |  | Make enum consistent (UML:class <<stereotype>> --> UML:enumeration) Check "String" data type from CIM, if exists, change to "string" | Change UML:class <<stereotype>> to UML:enumeration | [11 empty] | Closed
12 | Dwayne B. | 2018-01-09 |  | Enum |  | For enum classes, no ProtobufTag is needed but only ProtobufTag_Reserved if enum removed or updated | [12 empty] | Closed
11 | Larry L. | 2018-01-08 |  | Data Model |  | In BreakerDiscreteControlprofile we have modBlk, InterlockCheck, and syncroCheck as boolean, but shows as "anySimpleType" rather than Boolean in the image below. Did something slip on the list? It arose from Adam's question about I'm asumming that "unsigned char *" is optional[uint8_t] not uint8_t[]. searching for boolean in the EA Project gave the image below about it coming from XSD SimpleType. Is that correct ? | The “boolean” is a primitive data type which is translated to xsd:boolean (true/false) in xsd, and I assume it is translated into proto bool. I don’t know why it is defined as a list in the UML. And also why not translated into Boolean in the IDL. This may be a question for Andre. Also note there is another “Boolean”, capital “B”, defined in 61850. May need to align with Herb on its usage. | [11 empty] | Closed
10 | Larry L. | 2018-01-08 |  | Data Model |  | For qualities we have: in many measurement fields q Quality hexBinary and in Timestamp tq byte My recollection is both Qualtity and tq are 16bits long. Whatever their lengths, can we document their length in the field notes please? | And we may have to go back to Herb and document what each bit means. See Issue #14 | [11 empty] | Closed
9 | Dwayne B. | 2018-01-08 |  | Data Model |  | 1. ActivePower needs the protobuf tags 2. ENS_SolarStateKind - are the required/optional fields correct? stVal is marked as optional | Add tag should be required | [11 empty] | Closed
8 | Data Model Team Meeting (01/08) | 2018-01-08 |  | Schedule |  | Change end role multiplicity from 0..1 to 0..* for the ControlFSCH | [12 empty] | Closed
7 | Data Model Team Meeting (01/08) | 2018-01-08 |  | Protobuf discussion |  | Missing enum=0 in some enum classes. It is needed for Protobug generation. | Add “UNDEFINED (enum=0) for any enum classes that does not contain enum=0 field. | [11 empty] | Closed
6 | Shawn H. | 2018-01-08 |  | Module clean up |  | UML model still need more clean up to remove orphan classes and add notes as needed | [12 empty] | Pending
5 | Shawn H. | 2018-01-08 |  | ProtobufTag |  | ProtobufTag added as a tagged value for the ResourceReadingProfile and needed for all remaining profile after the review from SISCO team | [12 empty] | Closed
4 | Dwayne B. | 2018-01-03 |  | Role missing containment definition |  | I found a "shared" option on the following classes while using the RTI code generator: • generationStatusZGEN in GenerationStatus • loadStatusZGLD in LoadStatus • controlScheduleFSCH in ControlFSCC • essStatusZGEN in ESSStatus It looks like the "Containment" is missing on each of these relationships. | Fixed | [11 empty] | Closed
3 | Dwayne B. | 2018-01-02 |  | Missing enum value such as Ah |  | Is there a UnitSymbol for "Ah" anywhere in the original definition that we could add to the model? The SoC for an ESS ("SocAhr") is supposed to be represented in "Ah" but we don't have a value in the enum for that. | Ah added into the UnitSymbolKind which comes from CIM reading type (number 106) | [11 empty] | Closed
2 | Dwayne B. | 2018-01-02 |  | Missing ActivePower for GenertingUnit |  | We are missing the ActivePower class in our model (referenced from GeneratingUnit in the generation model). We probably just need to bring this class forward from our previous model. | ActivePower added | [11 empty] | Closed
1 | Dwayne B. | 2018-01-02 |  | Switch is a reserved word in several programming languages and cannot be used |  | In switchmodule, we have a class called "Switch" and this generates lines like the following in the IDL files: @nested(FALSE) struct SwitchControlProfile : openfmb::commonmodule::ControlMessageInfo { @key string targetSwitchSystemID; openfmb::switchmodule::SwitchControl switchControl; openfmb::commonmodule::IED ied; openfmb::switchmodule::Switch switch; }; @nested(FALSE) struct SwitchEventProfile : openfmb::commonmodule::EventMessageInfo { openfmb::switchmodule::SwitchEvent switchEvent; openfmb::commonmodule::IED ied; openfmb::switchmodule::Switch switch; }; @nested(FALSE) struct SwitchReadingProfile : openfmb::commonmodule::ReadingMessageInfo { openfmb::switchmodule::SwitchReading switchReading; openfmb::commonmodule::IED ied; openfmb::switchmodule::Switch switch; }; @nested(FALSE) struct SwitchStatusProfile : openfmb::commonmodule::StatusMessageInfo { openfmb::switchmodule::SwitchStatus switchStatus; openfmb::commonmodule::IED ied; openfmb::switchmodule::Switch switch; }; Notice the highlighted variables named "switch" above. Well, "switch" is a reserved word in several programming languages and cannot be used. I didn't even think about that previously. Changing that requires us to change the name of the "Switch" class but I'm not quite sure what to name it. Plus, if we change Switch, that also breaks our pattern that we have used with the other modules and profiles. | Wait for team discussion, but changed "Switch" to "ProtectedSwitch" | [11 empty] | Closed
0 | Dwayne & Larry | 2017-12-20 |  | Control Profiles |  | Rename <..>ControlProfile to <..>DiscreteControlProfile Leave <..>ControlProfile for control schedule | <..>DiscreteControl only applies to Swicth, Recloser and Breaker contril profiles | [11 empty] | Closed